|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| May | June | July | August | Sept | Oct | Nov | Dec |
| **Task:**Complete timeline.Obtain access to Working Group page.  | **Task:**Break Working Group into 5 sub-groups. | **Task:**Allow groups to identify and conduct preliminary research on projects they are interested in. | **Task:**Have one article drafted.Have groups elect one member to represent sub-group on monthly call.Have one speaker apply for GBA FMGL Conference.  | **Task:** Have sub-group coordinate and research project related to financial compliance (i.e. blockchain compliance framework [Picture something like NIST framework]) | **Task:**Have framework completed and work on presentation for FMGL | **Task:**Organize speakers and presenters of our year-end project for GBA FMGL  | **Task:**Continue rolling out the framework with a relevant article. |
|  | **Sub-Groups:**-Current evironment-Emerging trends-Financial Sector-POS/PCI-DSS Sector-Outreach | **Outcome:**Update and co-ordinate all sub-groups to make sure there is no duplication of efforts/work and encourage cross-functional collaboration.Allow subgroups to organize their own frequency of calls. | **Outcome:**Contribute to GBA awareness and foster participation across the group. | **Outcome:**By the end of Oct each sub-group has their portion of the plan shared with the group for peer review.Outreach would create communication plan for P.R. | **Outcome:** Be adequately prepared and ready for the GBA FMGL conference and framework rollout. | **Outcome:**Teach GBA FMGL attendees about the new framework | **Outcome:** Ensure adequate P.R. for the new framework.  |